Instructions and Template
For Base4NFDI Basic Service Proposals / Integration Phase / Version 2.4 / 2026-04-27

# General Instructions

The proposal template provides a mandatory structure and a number of tables to be completed. Apart from that, applicants may decide how to present the content. All sections of text in grey are intended to provide guidance for completing the proposal and should be deleted in your proposal submission.

Proposals for Base4NFDI Basic Services must be submitted via the spokesperson of the NFDI Section supporting the proposal to base4nfdi-office@lists.nfdi.de in PDF format. This implies that the proposal as well as results and work progress of the Basic Service has been presented and discussed in a Section meeting and was met with approval.

Further information about the next submission deadline and the whole evaluation process can be found at the Base4NFDI website, which will be updated continuously[1],[2]. Proposals must be written in A4 format, 11 pt Arial font with line spacing of 1.5. The length of the proposal may vary depending on the complexity of the proposed service but may not exceed 15 pages (excluding cover page, Gantt chart in chapter 5.2, financial tables of chapter 6 and appendix). A different font or line spacing may be used in tables, figures, footnotes and the list of references, provided the text is still easy to read. The proposal and appendices are to be written in English (BE). Please use the proposal template contained in part II of this form.
[1] https://base4nfdi.de/process/how-to-apply
[2] https://base4nfdi.de/process/decision-making

The requested funding amounts should not include programme allowances (for indirect project costs). Budgeted allowances will come from Base4NFDI flex funds and vary by the phase (Initialisation, Integration, Ramp-Up for operation) for which funding is requested.
Funding – with the exception of well-argued cases – will be limited to a maximum of two years and a maximum of €447.300,00 per year[3].
[3] An additional financial top-up to the stated amount - to compensate increased personnel costs based on updated DFG Personnnel Rates - is fully subject to the decision of the NFDI Consortia Assembly. For further information please refer to https://base4nfdi.de/process/how-to-apply, section “How much is funded per phase each year?” or contact base4nfdi-office@lists.nfdi.de in case of further questions.

For further information please refer to https://base4nfdi.de or contact Base4NFDI base4nfdi-office@lists.nfdi.de whenever answers are not available online.
Changes to version 2.2 of this document (2025-03-07) are highlighted with grey background colour. Change notes can be found on https://base4nfdi.de/resources/templates-logos. Please remove all remaining background highlighting for the final proposal.

We encourage you to publish your proposal (with or without funding tables) on Zenodo or similar, at some point after the submission.

For resubmissions, please make all changes visible, highlight revisions, and indicate how feedback from the first submission, e.g. the evaluation by the Technical Expert Committee, has been addressed.
# Proposal Template – Integration Phase
## General Information

- Name of proposed Basic Service (in English)
- Acronym of the proposed Basic Service
- Service "subtitle" explaining key functionality
- Corresponding NFDI Section
- Lead institution
The lead institution is the coordinating institute for the Basic Service for the current stage of	development.
Please enter the institute’s name and address.
Name of lead institution principal investigator
The primary contact and coordinator of the Basic Service.
Please enter the name and email address.
- Authors of the proposal
  [optional] Credit the authors of the proposal if their work is not otherwise acknowledged in this proposal.
- Participating institutions
Table 1: List of participating institutions
Principal Investigator	Institution, location	Contact E-mail	Member in [consortium][4]	Funding requested [yes | no]
[4] Name one DFG consortium the institution is or has a route to become a member of and through which funds should be appropriated if this proposal is approved.

List all participating institutions. If applicable, make clear if there are partner institutions	without funding.
- Initialisation Phase
  Provide information on the start date of the Initialisation phase, the planned runtime and the estimated end (month / year).
- Planned duration of the Integration phase
  The Integration phase typically runs 2 years.
- Statement on efforts required by consortia for integration of service
  Briefly explain what is required or what effort is needed by the consortia to integrate your service (time, personnel, technical, organisational or other requirements, etc.). This text will be presented as a short explainer to the consortia in the questionnaire, where they will vote on the proposal. (max. 200 words)
- Summary of the proposal in English and German
  up to 1,500 characters each, including spaces

## Summary of Initialisation Phase Results (max 3 pages)
This section provides a consolidated report of the initialisation phase, including progress, deviations, deliverables status, and readiness indicators. The information will also serve as input for evaluation of readiness for the integration phase.
### Change in Background and Motivation since the Start of the Initialisation Phase
Are there any changes compared to the proposal in the Initialisation Phase? If yes, please explain briefly, if no, please state ‘There are no changes compared to the proposal in the initialisation phase’.
If there have been any conditions or notes for the application for the Integration phase issued by the Technical Expert Committee in their proposal review for the initialisation phase, please share details on how these issues were addressed or resolved / what changes were made to the work plan?
### Results of Initialisation Phase
Please report on the status and results of initialisation phase work and on deviations from the proposed work plan. Please indicate explicitly whether any milestones or deliverables are not expected to be achieved or have not been achieved by the end of the Initialisation phase. If so, please explain why. Please also describe the work that still needs to be completed by the end of the initialisation phase in order to begin the orderly transition to the Integration phase.
#### Interim Report on Requirements for Finalisation of the Initialisation Phase
Please provide an overview on the Base4NFDI Initialisation Phase requirements - as listed below - for finalisation of the initialisation phase that reflects the current status of service development. The overview should contain information on the status of the required deliverables D.TA1.1 - D.TA1.5[5] in the form of a short summary, a list of outcomes (e.g., links to publications, repositories or other documentation) and if necessary an outlook on plans for completion until the end of the current phase. All relevant information should be in this proposal, while detailed information about the current state of your initialisation project will be documented in a report generated from OpenProject which will be passed on as an attachment to this proposal during its evaluation (including all required deliverables D.TA1.1 – D.TA1.7[6]).
[5] These deliverable notations were introduced by version 3.3 (after March 2025) of the Initialisation phase proposal template. If you applied with an earlier version of the template / prior to March 2025, these correspond to the deliverables 1.4.1 Requirements analysis, 1.4.2 Software evaluation, 1.4.3 Service design, 1.4.4 Service prototype and 1.4.5 Service piloting and user testing. Please contact the Base4NFDI team for more information.
[6] Initialisation phase proposal templates prior to version 3.3 do not have corresponding required deliverables for D.TA1.6 and D.TA1.7.
Further instructions on how to document the required initialisation phase deliverables can be found on Zenodo[7],[8]. The required deliverables contain information on target group definitions for the service, use cases and benefit descriptions per target group, results from preparational work, and preliminary concepts (e.g., technical, implementation and training).
[7] Base4NFDI - Requirements for Completion of Initialisation Phase https://doi.org/10.5281/zenodo.11519610
[8] Base4NFDI - HowTo: Reporting in Initialisation Phase https://zenodo.org/records/13384157
##### Requirements Analysis (D.TA1.1)
Due: 3 months after start date
Percent finished [via Open Project]:
Status: survey | analysis | report / planned | running | finished
Overview of relevant outcomes: Name/link to relevant outcomes. A comprehensive summary can be found in the Open Project attachment to this proposal.
Outlook: [If not finished 100 %, how do you plan to proceed?]
##### Software Evaluation (D.TA1.2)
Due: 6 months after start date
Percent finished [via Open Project]:
Status: analysis | report / planned | running | finished
Overview of relevant outcomes: Name/link to relevant outcomes. A comprehensive summary can be found in the Open Project attachment to this proposal.
Outlook: [If not finished 100 %, how do you plan to proceed?]
##### Service Design (D.TA1.3)
Due: 6 months after start date
Percent finished [via Open Project]:
Status: analysis | report / planned | running | finished
Overview of relevant outcomes: Name/link to relevant outcomes. A comprehensive summary can be found in the Open Project attachment to this proposal.
Outlook: [If not finished 100 %, how do you plan to proceed?]
##### Service Prototype (D.TA1.4)
Due: 12 months after start date
Percent finished [via Open Project]:
Status: prototype / planned | running | finished
Overview of relevant outcomes: Name/link to relevant outcomes. A comprehensive summary can be found in the Open Project attachment to this proposal.
Outlook: [If not finished 100 %, how do you plan to proceed?]
##### Service Piloting and User Testing (D.TA1.5)
Due: 12 months after start date
Percent finished [via Open Project]:
Status: piloting / planned | running | finished
Overview of relevant outcomes: Name/link to relevant outcomes. A comprehensive summary can be found in the Open Project attachment to this proposal.
Outlook: [If not finished 100 %, how do you plan to proceed?]
Attach a current version of the documentation in Open Project as an export in the form of a PDF report from the TA1 Work Space with up-to-date information on D.TA1.1 - D.TA1.5[9].
[9] Compare footnote 5.
#### Other
[Optional] Additional information on outcomes of the Initialisation phase (e.g. the number of workshops and/or educational events provided and resources (documentation, reports, designs, training,...) published if not covered above) or if there is something relevant to report on D.TA1.7 (Base4NFDI outreach events).
### Update on Technical Readiness Level (TRL) of the Proposed Basic Service
Please provide an updated Technical Readiness Level (TRL) of the proposed Basic Service. Supply a TRL of the current version of your Basic Service framework (at the time of application for integration) and the targeted TRL by the end of the initialisation phase and the targeted TRL by the end of the integration phase. The required minimum TRL to enter the Integration phase is 5-6[10]. For the definition see the initialisation phase template[11]. Provide a brief statement (max. 500 characters) summarising your current assessment of achievements in relation to the TRL planning, comparing planned TRL progression with the current state of implementation. Highlight supportive and hindering circumstances.
[10] https://base4nfdi.de/process/criteria-for-basic-services
[11] Most recent version can be downloaded from: https://base4nfdi.de/resources/templates_logos
For services with a non-technical focus (e.g. consulting, training, standards, or information services), please refer to the notes in “Service integration procedures”[12] on how TRLs can be interpreted in such contexts.
[12] Report on Base4NFDI service integration procedures, https://zenodo.org/records/17206953

## Working Concept for the Development of the Basic Service (max 2.5 pages)
Describe the overall concept for the development of the Basic Service with regard to the Integration and Ramp-Up phase. Describe the Integration phase in more detail. Note that for the Integration phase the involvement of the consortia, the first outline of a business and operational model and concepts for training (relating to identified target groups and content) as well as outreach need to be addressed.
### Service Integration Concept
Describe in particular the integration with the services of the partner consortia. Also address your strategy to ensure interoperability with relevant consortia services (e.g., workshops, incubators, engagement). Summarise your awareness of how your service engages with the NFDI landscape at technical, semantic, organisational and / or legal level - based on the findings from the initialisation phase, including which services your basic service complements or depends on within and outside NFDI. Where applicable, describe how your service is built based on commonly accepted community standards.
Provide information on status and/or plans of uptake of the service in NFDI Consortia, e.g. provide the name of the NFDI Consortium and describe in brief the status of contact, work in progress, possible incubators, possible planning, and/or other means of integration. Where applicable, also describe planned integrations beyond NFDI.
What key performance indicators (KPIs) will be used to measure the success of your service by the end of the Integration phase? Consider basic technical KPIs for your service but also in regard to communication and training activities. Please remember that during the Ramp-Up phase, the service needs to scale to a larger user group. Clear estimates for requirements should be determined by the end of the Integration phase. We recommend that you consider a consultation with the Base4NFDI team, e.g. the Service Stewards and TA2, on this topic.
The results of the Integration phase need to be made available via an open license. Please explicitly confirm that your service still complies with the openness concept. If you see a necessity to change the openness concept of your service (e.g., use of non-openly licensed software components, restrictions on openly licensed publication of code or other output, or the incorporation of proprietary software), you need to explicitly state the reasons.
Please provide initial or updated information on accessibility measures in your service. Consultation of the project’s accessibility guidelines[13] or staff is recommended if needed.
[13] Base4NFDI– Guidelines on Application of Web Accessibility; https://zenodo.org/records/15719661
Please clarify any changes regarding overlap with EOSC EU Node services[14], taking into account the development of new services within the EU Node and provide an updated assessment if you service will be complementary, overlapping, or an entirely new offering. Are there further International partnerships or collaborations in place or planned?
[14] https://open-science-cloud.ec.europa.eu/services
### Future Development and Ramp-Up Outlook
Describe the envisaged transition to the Ramp-Up phase. Please describe which quality criteria you consider relevant for your service (e.g., what users can and cannot expect, availability, support, uptime, etc.) and how your business model for eventual service provisioning would look like.
How do you envisage your service becoming interoperable with the EOSC EU services[15] or describe any plans to integrate with or reuse elements of these services. A comprehensive summary is provided in this policy paper[16]. Describe any other existing relations with EOSC (e.g., have you worked with task forces of EOSC or are you planning to be involved?). Add any events (conferences or hackathons) you attended or plan to attend in the EU context.
[15] https://open-science-cloud.ec.europa.eu
[16] Base4NFDI Policy Paper: "Base4NFDI Services and EOSC: Guidance for Interoperability", Version 1; https://zenodo.org/records/13946300
### Risks and Challenges
Give an update on the risks and challenges that may occur through operations of the service on behalf of the Integration or Ramp-Up phase.
Describe the main risks that could affect the success of the project. For each risk, assess its likelihood (e.g., low, medium, high) and severity (e.g., minor, moderate, critical). Include a clear mitigation strategy to reduce the potential impact or likelihood of each risk. Risks may be technical, organizational, financial, regulatory, or related to external dependencies. Use a table or list format for clarity.
Table 2: Risk Management
Risk Description	Likelihood	Severity	Mitigation Strategy
Describe the potential issue	e.g., medium	e.g. high	Describe how the risk will be managed or reduced
Godzilla eats the computing centre	rare	very high impact	Full off-site backup copies will ensure a possible rebuild of the system
...

## Support Actions from Base4NFDI / NFDI Sections, and Integrating NFDI Consortia / Efforts (max 1 page)
Base4NFDI will offer support on overarching aspects of service development (e.g., training, user experience and testing, community engagement and networking). Please specify the additional support you explicitly need from the Sections and from Base4NFDI or any other support. An example is shown in Table 3.
Table 3: Support needed from Base4NFDI / Service Stewards / Section
Support from	Work package / Description of contribution	Contact person
Base4NFDI	Support organising workshop/training	Lara Mustermann, Musterinstitut, lara.mustermann @musterinstitut.de
Section Metadata		Lara.mustermann@mustermail.de
...

Please describe the contributions required from each consortium to integrate the Basic Service with their respective consortium services. If these are common to all, please provide a list of all the consortia that will integrate the Basic Service in the Integration phase. A letter of commitment from these consortia is required.
Table 4: Contributions required from the integrating consortia
Support from	Involved effort	Consortium (contact)
Consortium 1	Provision of resources, participation in incubator project	Max Mustermann, Musterinstitut, max.mustermann@mustermail.de
Consortium 2
...

## Work Programme (ca. 6 pages)
This section should describe the structure of your work programme for the Integration phase as it relates to the overall objectives of the proposed Basic service.
### Overview of Work Packages
The work programme for the integration of a Basic Service is divided into different work packages, deliverables, and milestones within. Please add all institutes working in a work package and the institute leading the work package. An overview of what is expected from a basic service in each phase can also be found on our website[17].
[17] https://base4nfdi.de/process/what-is-expected-for-each-phase
We recommend a work package on community engagement and communication to allocate resources to, for example, the realisation of but also participation in workshops. Special attention should be paid to centrally coordinated activities and offers by Base4NFDI staff like a monthly Jour Fixe with Base4NFDI and the other service teams, regular, needs-driven consulting regarding training, with a focus on training curation, curation and piloting - continuing the target group and learning goals definition from the Initialisation phase. Resources should be put aside for EOSC interoperability activities. It is expected the team will contribute to a checklist for EOSC interoperability and an EOSC Connectivity meeting during the phase organised by the Base4NFDI team. This also includes being aware of developments of onboarding resources to EOSC documentation from the EOSC Association and other relevant frameworks relevant to the particular service.
Please consider these requirements when planning your work programme for the Integration phase:
- Deliverable D.Int.1: Documentation of service integration and success
- Deliverable D.Int.2: Documentation of service maturity
- Deliverable D.Int.3: Documentation of sustainability
- Deliverable D.Int.4: Provision of service portfolio metadata
- Deliverable D.Int.5: Self-assessments of software quality
- Deliverable D.Int.6: Documentation of usability
- Deliverable D.Int.7: User-centred documentation and training
- Deliverable D.Int.8: Short overview about the outcomes of the Integration phase and presentation in a section meeting
- Deliverable D.Int.9: Participation in Base4NFDI outreach events

For more information please see the detailed requirements documentation[18] or contact the Base4NFDI team for consultation.
[18] Requirements for Completion of the Integration Phase. https://zenodo.org/records/17107045
Note that deliverables are tangible outcomes of the work (software, documents, plans, designs, training material…), while milestones can signify conceptual changes or specific moments in time. Here the achievement of the goals of one of the development phases and the transition to the next phase is considered a milestone.
Please add the nine Base4NFDI deliverables to your work plan (with their original notation), preferably as a separate work package, with relations to your own work packages. Alternatively to a separate work package you may include them into your own, but keeping their names and notations.
Table 5: Overall work programme with work packages, deliverables, milestones, and responsible partner.
Work package	Deliverables (D) and milestones (M)	Responsible partner	Related work packages
1. content	D1.1 / D1.2 / M1.1 / ...	institution
2. other content	D1.1 / D1.2 / M1.1 / ...	Some other institution
...	...	...
9. Base4NFDI mandatory items	D.Int.1 Documentation of service integration and success
	D.Int.2 Service maturity report
	D.Int.3 Documentation of sustainability
	...

### Detailed Work Programme
Please provide a detailed description of the work packages, using one subsubsection per work package. Please include a Gantt chart summarising the duration, dependencies, deliverables and milestones of the WPs. The Gantt chart should be integrated with the proposal but will not be added to the total page count.
#### WP1
#### WP2
#### WP3
## Funding Request
List the task area in the table heading and the individual work packages in the table. Add additional lines as necessary.
Table 6: Funding request by work package
	Year 1	Year 2	Total (in €)
Work package 1
Work package 2
Work package 3
...
Total project funds

List the name of each institution, adding additional lines if necessary.
Table 7: Funding request by institution
	Year 1	Year 2	Total (in €)
Institution	Totals in €
Lead institution
Participating institution 1
Participating institution 2
Participating institution 3
...
Total project funds

Please note the current staff funding rates of the DFG at the time of application, only on this basis funding is possible[19]. In addition, please keep in mind the maximum budget that can be requested in the Integration phase (cf. Section I).
[19] https://www.dfg.de/formulare/60_12/
Any proposed instrumentation funding must be explained separately below the table.
Table 8: Funding request by funding category
	Year 1	Year 2 / (if applicable)	Total (in €)
DFG funding category	Totals in €
Staff
Direct project costs
Total project funds

List the number of person months for which funding is requested under the given staff categories of the DFG Personnel Rates.
Table 9: Funding request by staff category
	Year 1	Year 2 (if applicable)
Staff category	Number of person months	Number of person months
Postdoctoral researchers / and comparable
Doctoral researchers / and comparable
...

### Other Funding Sources
Please indicate whether the proposed service itself has already received or is currently receiving funding by Base4NFDI or other sources, or whether partners have received funding specifically for this service. In particular, specify any past, current, or planned funding related to the development of the service, to ensure clarity on what is to be financed within this proposal and to avoid overlaps (especially with DFG funding).
### Exit Strategy
In case you are not eligible for further Base4NFDI funding after the integration phase ends, describe how you will continue or terminate the basic service and its development. Describe, if applicable, what other funding might be used to continue development. Describe how you will secure the results achieved within the integration phase (e.g. reports, presentations, articles, code, webservices etc.). Describe how personal data collected by the service will be handled after the integration phase. Which stakeholders need to be notified about the changed funding situation and any potential resulting updates to the service? Which PI/ applicant institution will be responsible for the basic service after the project terminates?

On the following page you will find a template to confirm the accuracy of the information provided in this application (Principal Investigator) as well as the commitment of all participating institutions (institute directors) listed in section "1 General information". You can reproduce the template accordingly. Please provide confirmation for the lead and every participating institution listed in Table 1.
[NAME OF INSTITUTION]

We herewith certify that we have submitted this proposal to Base4NFDI and that the information provided therein is accurate.

Head of the lead / participating institution

_____________________________	_____________________________
First name last name	City, date, signature

Principal Investigator

_____________________________	_____________________________
First name last name	City, date, signature

# Appendix
The appendix may only include the following information and documents:
##### Acknowledgement
Any acknowledgements, e.g. to identify a research funder or grant id, should be placed in a separate section immediately before the reference list.
##### Bibliography and list of references
Please list all sources and data repositories, information infrastructures and software that you have used to describe the status quo in your proposal. Indicate which sources were written or developed by members of the participating institutions (for example, by highlighting the source in bold).
##### Letters of commitment (LoC) supporting the Basic Service development (cf. section 4 of this form)
It is standard for project partners to commit to the project activities. Partners are named in the paragraph "general information - participating institutions" of this template. Letters of commitment (LoC) are requested only in three cases: 1) from an NFDI consortium that commits to co-develop the service with consortium funds a LoC should detail the specific contributions of this consortium to the service, and/or 2) from an NFDI consortium that commits to use the service a LoC should outline the concrete steps to be taken by this consortium towards this goal, or 3) from other persons or institutions - also external to the NFDI - that do not actively participate but contribute to the service in any form.
LoCs can be submitted until two weeks after the application deadline.

Please do not provide generic consortia support letters. General support including the approval of 50% of the NFDI consortia will be requested in a separate process by the Base4NFDI coordination team.